## Test case
REDIFF MAIL
Version: |  | Environment Details: Windows10,Chrome |  |  | Tested by:Athullya P D
Verified by: |  | Module name:Registration |  |  | Date:28/03/25
Test id | Test Description | Test procedure | Test data | Expected result | Actual Result | Status
RM_REG_001 | Check whether the url is loading properly | 1.Enter the Url in the url field and press enter | https://register.rediff.com/register/register.php?FormName=user_details | Open Rediff mail as expected | Opened rediffmail registration page as expected | PASSED
RM_REG_002 | Check whether all lables ,textboxes,buttons,iconsand links are available as per the client requirement | 1.Cross check the client requirement sheet with the page |  | All fields are available as client requirement | All fields are available | PASSED
RM_REG_003 | Check whether the alignment of all textboxes,lables,buttons are proper and uniform or not | 1.Open the url 2.Check the alignment of all labels,textarea |  | All fields and labels are in uniform as client requirenment | All fields and labels are in same size | PASSED
RM_REG_004 | Check whether the spellings of the content in the page are correct | 1.Open url 2.Check online spelling checking tool and check the spelling are correct |  | Spellings of content in the page are correct | spellings are correct | PASSED
RM_REG_005 | Check whether all fields are accepting values and are editable | 1.Open url 2.Type values in every field 3.Make changes in the already entered values |  | All fields are accepting values and are editable | fields accepting data | PASSED
RM_REG_006 | Check whether the name field is only accepting alphabets or not | 1.Ope url 2.Type the test data | Anu Agks56% | When an user type anyting other than alphabets an error popup should arise | error message is showing | PASSED
RM_REG_007 | Check whether the name field accept values only upto 30 characters or not | 1.Locate the name field 2.Type 31 characters name | ann catherin elizabath mary joseph david fernadez | An error message should show | error message is not showing the data is accepting | FAILED
RM_REG_008 | Check whether the name field can only accpt upto 2 spaces or not | 1.Locate the name field 2.Type more than 2 spaces | anu davis anthony sdf | An error message show like that name field should not accept more than 2 spaces | accepting 2 spaces | PASSED
RM_REG_009 | Check whether the pasword field accept only the password according to the specified criteria | 1.Locate password field 2.Type a pasword as per the requirement and not | anu davis fg25jk Qwerty123@ | An error popup should appear when the password does not neet the requirement specified | error is showing | PASSED
RM_REG_010 | Check whether the password and confirm password fields match, and show an error immediately if they do not match during input. | 1Locate the password field 2.Type the password | Qwertyu123@ | An error popup should appear when the password and confirm password fields are not same | Error is only showing when the create account button is clicked | FAILED
RM_REG_011 | Check whether the email field should not accept mail extensions and spaces or not | 1.Locate the email field 2.Type an email 3.Click the check availability button | anudavis anudavis@gmail.com | An error popup should appear when email field occupy the mail extension and spaces , | Error is displayed when anything other than the specified format is typed | PASSED
RM_REG_012 | Check whether the check availability button is working and check if the mail is already created r not | 1.Locate the email field 2.Type an email 3.Click the check availability button | anudavis | check availabilty button should work and show message if the mail is alreay taken | Tehe availablility is showing and suggestions are also showing | PASSED
RM_REG_013 | Check whether the drop down of the date of birth field is properly working or not | 1.locate the drop down 2. Randomly select any date of birth | 30-07-1995 | Show an error message if nothing is selceted or any of the date/month/year is not selected | The drop down is accepting a date not in a month and error only show when create button is clicked | PASSED
RM_REG_014 | Check whether the radio button against the gender field is selecting any of one gender at a time | 1.Locate the gender field 2.Toggle the selection | female | The selcted item should be heighlighted | only one dender is selecting at a time | PASSED
RM_REG_015 | Check whether the drop own against the label I live in properly scrollable to the end and when it is below the end of screen should be visible to thetop accordingly and selected thing should be heighlighted | 1.Locate the country field 2.croll up and down 3.Select the counrtry required | India | The selcted item should in the field | scrolling is proper and all cities are visible | PASSED
RM_REG_016 | Check whether the alternative email field only accept a validate email address with all proper extensions | 1.Type an Email address | anuji.com anu@gmail.com,anu@co.in,anu@service.net | An error should how if the mail address is not validate | All email extension are accepting | PASSED
RM_REG_017 | Check whether the checkbox "I don’t have a valid email" is clickable, and upon clicking, the alternative email field should be hidden. | 1.check the checkbox 2.mail field is hide after clicing it the checkbox |  | The email field should hide after clicking the checkbox | Field is hiding when the check box is clicked | PASSED
RM_REG_018 | Chek whether the drop down of country code in phone number field is navigatable and the field only accpt number up to country standard limit and error should show when anything is typed other than the country standard at the time of inserting | 1.Select the proper country code 2. type the phone number | 9562212969 | An error message should come if the phone number doe not follow each country std and if type anything other than digits | Mobile number field is accepting more than the country standard digit and only showing error when the create button is clicked | FAILED
RM_REG_019 | Check wther the captcha field is changing every time the page is refreshed or not | 1.Refresh the page and check the captcha is changing or not |  | The captcha should change at every time page is refrehed | captcha is refreshing | PASSED
RM_REG_020 | Check whether the captcha field is accepting characters and as same of the captcah as in image or not | 1.Type captcha 2.click the create my account button |  | An issue should arise incorrect captcha and captcha should be refreshed | Error is only showing when the create account button is clicked | FAILED
RM_REG_021 | Check whether the user is already registered by using the mail id and phone number is already taken or not | 1.Type values in email field and phone number 2.fill the form 3.click on the create button |  | Show an message if the uer is already register asa ginst the phone number and email id | Already registered users can not create account | PASSED
RM_REG_022 | Check whether the privacy policy and terms and conditions are navigating into its appropriate page and when mouse hover it show an underline | 1.Click the terms & conditions, privacy&policy |  | the page should navigate to its proper page | privacy and policy is navigating to its corresponding pages | PASSED
RM_REG_023 | Check whether the logo icon is navigating to the home page | 1.click the logo 2.check it is navigating to home page |  | Logo should redirect the the home page | Logo is navigating to home page | PASSED
RM_REG_024 | check whether the phone number is accepting 10 digits or not | 1.Locate phone number field 2.type more /less 10 numbers |  | error message should come at the time of insering more or less digits | Error is only showing when the create account button is clicked | FAILED
RM_REG_025 | Check whether the date of month does not exceed the limit and show an error message at the time of selecting the dob | 1.Locate dob fielld 2.Type a unavailable date for a month | 30-02-2005 | show an error message at the time of entering the dob | only showing when click on create account button error message should show at the selection | FAILED
RM_REG_026 | Check whether the cross mark should disable from the email field click any of suggested options | 1.Locate the email field 2.type any tetvalues 3.click the check availability 4.selcete any of the suggested options | abcs | the cross mark should disable after selecting any of the suggested one | cross mark is showing after selecting valid one | FAILED
RM_REG_027 | Check whether otp is sending to the phone number properly or not | 1.Type the phone number in the corresponding field |  | otp should be delivered to the regitered phone number | otp is coming | PASSED
RM_REG_028 | check whether when select 'other " option in where you live ,a new field should appear for writing city | 1.select the country where you live in 2.select the other option in the city field 3.type the city | cochin | a new field should come when select the other option in the city field and should be writable | field is coing and writable data | PASSED
RM_REG_029 | Check whether the other city field only accept alphabets or not | 1.Type the other from city option 2.type a city name | jkjj67 | a error message should come when anything type other than alphabets | error message is showing only when the create button is clicked | FAILED
RM_REG_030 | Check whether the recovery email id only accept proper mail id | 1.Locate the email field 2.Type an email | ghjk.vo8 ann@gmail.com | a error message should come at the time of inserting a not valid email id | error message is only coming the create button is clicked | FAILED
RM_REG_031 | Check whether security question answer is masked or not | 1.select any security question 2.type the answer in the field |  | The answer of of security question is masked | The answer is masked | PASSED
RM_REG_032 | Check whether the answer of security question should only accept the data according to the question | 1.select any security question 2.type the answer in the field | ghjj24(security question- school name) | The field should accept data according to the question | the school name field is accepting numbers | FAILED
RM_REG_033 | check whether the data entered in security field question is masked | 1.select any security question 2.type the answer in the field |  | the data should masked | a field like Mother's Maiden Name is coming and are accpeting digits also and the data is not masked also | FAILED
RM_REG_034 | Check whether the phone number field is editable while the otp is validating and can send new otp | 1.Complete registration 2.send otp and move to otp validating page 3.edit the mobie number |  | The mobile can be edited and resend otp | The new otp can't send from that page | FAILED
RM_REG_035 | Check whether otp is sending to the phone number after it corrected | 1.Complete the form 2.click create button 3.check the mobile whether the otp received or not |  | The otp should receive in the registered mobile | otp is receiving | PASSED
RM_REG_036 | Check whether the gender field has the options: Male, Female, Other, and Prefer not to say. | 1.Launch url 2.locate gender options |  | The gender options should have 3 options | Only 2 options are available | FAILED
RM_REG_037 | Check whether the page is responsive or not | 1.Lauch url in random different devices |  | The layout and content should appear properly | The layout of the proper in different devices | PASSED
RM_REG_038 | check whether the page is secured or not | 1.Launch url 2.locate the urls have https |  | The url shoud start with https | The url is secured and started with https extension | PASSED
RM_REG_039 | Check whether the page is user friendly or not | 1.Launch url |  | The user should not have any confusions while seeing the site | There is no confusions in the url | PASSED
RM_REG_040 | Check whether the "Create" button remains disabled until all mandatory fields are correctly filled. | 1.Launch url 2.Locate create button |  | The button is should be disabled first and enabled only after all mandatory fields are filled | In the site the button is enabled from the beginning | FAILED
RM_REG_041 | Check whether the page reloads automatically after the network connection is restored following an interruption | 1.Launch url 2.interrupt network |  | The page should reload automatically without clicking reload button | The site only reloading after the reload is clicked | FAILED
RM_REG_042 | Check whether offline form submission is prevented | 1.Launch url 2.fill all fields 3.interrupt network 4.click create button |  | The submission should not be done | The form is not submitting in offline mode | PASSED
RM_REG_043 | Check whether the form behaves properly in landscape and portrait modes on mobile devices. | 1.Launch url in lanscape and portait mode in mobile |  | The layout should be proper in both modes | The layout is fine in both modes | PASSED
RM_REG_044 | Check whether keyboard navigation is possible | 1.Launch url 2.use enter key to submit ,use arrows |  | The navigation and form submissions should occur using keys | Keybord navigation is working | PASSED
RM_REG_045 | check whether the session expire after particular time or not | 1.Launch url 2.Use same pge for a time |  | The session should expire after particular time | The session is not expiring after a long time | FAILED
RM_REG_046 | ensure the page is only launching when network is good | 1.Launch url |  | The url should only launch in online | The page is opening only in online | PASSED
RM_REG_047 | Check whether browser back button does not resubmit the form data after form submission. | 1.Launch url 2.fill all fields 3.click create button 4.click back |  | The data should not resubmit | Clicking the back button prompts a data resubmission request. | FAILED

## Bug report
REDIFF MAIL
Version of the application: |  |  | Environment Details:Windows11,Chrome |  |  | Reported by:Athullya P D
Reported to:Viji Venughopal |  |  | module Name:Registration page |  |  | Date:03/04/25
Bug id | Test id | Bug description | Expected result | Steps to reproduce | Evidence | Severity | Priority | Status
DEF_RM_REG_001 | RM_REG_007 | The fullname field is accepting more than 30 characters | Full name field should not accept more than 30 characeters | 1.Open the website 2.Type more 30 characters |  | Major | High | New
DEF_RM_REG_002 | RM_REG_010 | Error is not showing when the password & confirm passwords are not same it only appear create account button is clicked | An error popup should appear when the password and confirm password fields are not same | 1Locate the password field 2.Type the password |  | Major | High | New
DEF_RM_REG_003 | RM_REG_018 | Mobile number field is accepting more than the country standard digit and only showing error when the create button is clicked | An error message should come if the phone number doe not follow each country std and if type anything other than digits | 1.Select the proper country code 2. type the phone number |  | Major | High | New
DEF_RM_REG_004 | RM_REG_020 | Error is only showing when the create account button is clicked for incorrect captcha | An issue should arise incorrect captcha is entered | 1.Type captcha 2.click the create my account button |  | Major | High | New
DEF_RM_REG_005 | RM_REG_024 | The error is shown only when the 'Create Account' button is clicked with a phone number having more or less than 10 digits for India as the country code | error message should come at the time of insering more or less digits | 1.Locate phone number field 2.type more /less 10 numbers |  | Major | High | New
DEF_RM_REG_006 | RM_REG_025 | The error message is showing at the time inserting a unavailable date against a month | When user selects the unavailable date in a month its should show error message at the time of inserting it selft | 1.Locate dob fielld 2.Type a unavailable date for a month |  | Major | High | New
DEF_RM_REG_007 | RM_REG_026 | A cross mark is still showing even after selecting a valid option from the suggested emails in the Rediff mail field | the cross mark should disable after selecting any of the suggested one | 1.Locate the email field 2.type any tetvalues 3.click the check availability 4.selcete any of the suggested options | https://drive.google.com/file/d/1FzGP9gK16OGzeI9aDnLp21H1jPyW3Abp/view?usp=drive_link | Minor | Medium | New
DEF_RM_REG_008 | RM_REG_029 | The city field accepts characters other than alphabets, and the error is not shown instantly | a error message should come when anything type other than alphabets | 1.Type the other from city option 2.type a city name |  | Minor | High | New
DEF_RM_REG_009 | RM_REG_030 | The error is not showing when the email ID is invalid; the error message appears only after clicking the Create button | a error message should come at the time of inserting a not valid email id | 1.Locate the email field 2.Type an email |  | Major | Medium | New
DEF_RM_REG_010 | RM_REG_032 | In the security question, each question is accepting invalid data | The entering data should be match to the corresponding question | 1.select any security question 2.type the answer in the field | https://drive.google.com/file/d/1ai6hlt3rKVt6X2SGodKKSyreuUM0UB-1/view?usp=drive_link | Major | High | New
DEF_RM_REG_011 | RM_REG_033 | A field like Mother's Maiden Name is appearing, and it is accepting digits as well; also, the data is not masked | the data should masked | 1.select any security question 2.type the answer in the field | https://drive.google.com/file/d/1ai6hlt3rKVt6X2SGodKKSyreuUM0UB-1/view?usp=drive_link | Major | High | New
DEF_RM_REG_012 | RM_REG_034 | The new otp can't send from that page | OTP should send to the mobile after editing | 1.Complete registration 2.send otp and move to otp validating page 3.edit the mobie number |  | Major | High | New
DEF_RM_REG_013 | RM_REG_036 | Gender field should have 3 options | Only 2 options are available | 1.Launch url 2.locate gender options |  | Minor | Medium | New
DEF_RM_REG_014 | RM_REG_040 | "Create" button remains enabled before all mandatory fields are correctly filled. | The button is should be disabled first and enabled only after all mandatory fields are filled | 1.Launch url 2.Locate create button | https://drive.google.com/file/d/1fGplK0egnCPquIr9VvL3LxZLYrvbC-9k/view?usp=drive_link | Moderate | Low | New
DEF_RM_REG_015 | RM_REG_041 | The site only reloading after the reload is clicked | The page should reload automatically without clicking reload button | 1.Launch url 2.interrupt network |  | Minor | Medium | New
DEF_RM_REG_016 | RM_REG_045 | The session is not expiring after a long time | The session should expire after particular time | 1.Launch url 2.Use same pge for a time |  | Moderate | High | New
DEF_RM_REG_017 | RM_REG_047 | Clicking the back button prompts a data resubmission request. | The data should not resubmit when click on back button | 1.Launch url 2.fill all fields 3.click create button 4.click back | https://drive.google.com/file/d/17jK8Z7Hie-MyepwXAkpxXANaFF9Vlak3/view?usp=drive_link | Major | High | New